## Slide 1
Software engineering (Undergraduate)
Course Name software engineering
CSC 3114
(Undergraduate)
Chapter 08 software project estimation
Mahmudul Hasan (Mahmud)
mahmudul@aiub.edu

## Slide 2: Software project planning
The overall goal of project planning is to establish a pragmatic strategy for controlling, tracking, and monitoring a complex technical project.
WHY?
So the end result gets done on time, on budget, and with quality
Slide-2

## Slide 3: project planning task set-1
Establish project scope
Determine feasibility
Analyze risks
Define required resources
  Determine require human resources
  Define reusable software resources
  Identify environmental resources
Slide-3
Off-the-shelf: Available in the stock, reuse as it is

## Slide 4: project planning task set-ii
Estimate cost and effort
  Decompose the problem
  Develop two or more estimates using size, function points, process tasks (complexity),
  Reconcile the estimates
Develop a project schedule
  Establish a meaningful task set
  Define a task network
  Use scheduling tools to develop a timeline chart
  Define schedule tracking mechanisms
Slide-4

## Slide 5: Project estimation Principles
Project scope must be understood
Elaboration (decomposition) is necessary
Historical metrics (pervious data) are very helpful
At least two different techniques should be used
Uncertainty is inherent in the process
Slide-5

## Slide 6: Conventional Method
Conventional estimation techniques
  task breakdown and effort estimates
  size (e.g., LOC/FP) estimates
  compute LOC/FP using estimates of information domain values
  use historical data (previous experience) to build estimates for the project
Automated tools
Slide-6

## Slide 7: Effort estimation
A dynamic multivariable model for effort estimation
E = [LOC x B0.333/P]3 x (1/t4)
Where,
E = Effort in person-months or person-years (the amount of time, personnel devote to a specific project)
t = Project duration in months or years
B = Productivity Factors
P = Productivity Parameter

## Slide 8: COCOMO (Constructive Cost Model)
Based on SLOC characteristic, and operates according to the following equations:
Effort = PM = Coefficient<Effort Factor>*(SLOC/1000)^P [100,000 SLOC/1000 = 100k SLOC]
Development time = DM = 2.50*(PM)^T
Required number of people = ST = PM/DM
PM : person-months needed for project (labor working hours) SLOC : source lines of code P : project complexity (1.04-1.24) DM : duration time in months for project (week days) T : SLOC-dependent coefficient (0.32-0.38) ST : average staffing necessary
Software Project Type | Coefficient <Effort Factor> | P | T
Organic | 2.4 | 1.05 | 0.38
Semi-detached | 3.0 | 1.12 | 0.35
Embedded | 3.6 | 1.20 | 0.32

## Slide 9: COCOMO (Constructive Cost Model)
Organic: relatively small, simple software projects in which a small teams with good application experience work to a software development project (e.g. showing VUES information to webpage)
Semidetached: an intermediate (in size and complexity) software project in which teams with mixed experience levels works in a mix of hardware and software application (e.g. biometric log-in time saved in VUES database)
Embedded: A software project that must be developed within a strongly coupled to hardware environment (e.g. biometric device, elevator)

## Slide 10: Make-buy decision

## Slide 11: Computing expected cost from decision tree
((path probability) x (estimated path cost)
expected cost =
i
i
For example, the expected cost to build is:
expected cost = 0.30 ($380K) + 0.70 ($450K)
similarly,
expected cost = $382K
expected cost = $267K
expected cost = $410K
reuse
buy
contr
= $429 K

## Slide 12: references
R.S. Pressman & Associates, Inc. (2010). Software Engineering: A Practitioner’s Approach.
Kelly, J. C., Sherif, J. S., & Hops, J. (1992). An analysis of defect densities found during software inspections. Journal of Systems and Software, 17(2), 111-117.
Bhandari, I., Halliday, M. J., Chaar, J., Chillarege, R., Jones, K., Atkinson, J. S., & Yonezawa, M. (1994). In-process improvement through defect data interpretation. IBM Systems Journal, 33(1), 182-214.
Slide - 12